## Sheet1
Date | Item | Percent
2022-02-25 | Created testing room. Started collision. Making eveything IGameObject and giving everything a hitbox | 100%
2022-02-28 | Collision iterator and detector works | 97%
2022-03-02 | Parser for maps started. CSV maps started | 95%
2022-03-04 | Finsihed CSV maps. Running parser. Collision nearly complete. Room transitions | 90%
2022-03-05 | Cleaning up code, mouse implemented, room implemented. | 85%
2022-03-07 | Optimization of code and getting rid of magic numbers. Link takes damage from proper sources | 70%
2022-03-08 | Enemy health and item attack. Changed bat AI. Fixed link's damage color | 40%
2022-03-09 | Updated behavior to account for projectiles. Breakable walls. Items pass through room blocks | 30%
2022-03-10 | Adjusted sprites. Code cleanup | 10%