## Sheet1
Dates | Percent | Item
2022-04-04 | 95% | Portal gun started
2022-04-06 | 85% | Portal gun finished
2022-04-11 | 60% | BUGS FIXED, pause screen, menu screen.
2022-04-12 | 50% | Overworld imported and created
2022-04-13 | 45% | New ISpriteRotatable and Skeletron sprites imported
2022-04-14 | 40% | Skeletron finished and beginning dragon bullet hell
2022-04-15 | 35% | Victory screen and skeletron updates
2022-04-17 | 34% | Fixed QuadShot
2022-04-19 | 30% | Code cleanup and boss fight entrance
2022-04-20 | 25% | Fog of war fully implemented
2022-04-22 | 15% | More bug fixes
2022-04-24 | 0% | Finished hardcore mode and polish